## Renovation Quote
CONTRACTOR'S RENOVATION QUOTE
Hotel Renovation Project · Remediation Works · Task 2 Data
Room Number | Room Name (English) | Room Name (Chinese) | Work Type | Job Description | Contractor Qty | Unit | Unit Price (CNY) | Contractor Total (CNY) | Inspector Approved Qty | Notes
5 | Small Dining Room | 小餐厅 | Floor repair | Ceramic floor tile replacement | 80 | m² | 220 | 17600 | 40 | ⚠ Approved qty: 40
5 | Small Dining Room | 小餐厅 | Wall finish | Interior wall paint | 40 | m² | 85 | 3400 | 40
5 | Small Dining Room | 小餐厅 | Drainage | Drainage channel repair (lump sum) | 1 | item | 18000 | 18000 | 1
8 | Kitchen | 厨房 | Waterproofing | Polyurethane waterproofing membrane | 96 | m² | 450 | 43200 | 48 | ⚠ Approved qty: 48
8 | Kitchen | 厨房 | Floor repair | Cement floor screed | 48 | m² | 280 | 13440 | 48
8 | Kitchen | 厨房 | Wall repair | Cement render to lower wall zones | 38 | m² | 320 | 12160 | 24 | ⚠ Approved qty: 24
8 | Kitchen | 厨房 | MEP works | Gas pipe rerouting (lump sum) | 1 | item | 23500 | 23500 | 1
11 | Salon | 理发室 | Electrical | First-fix electrical rewire (lump sum) | 1 | item | 64000 | 64000 | 1
11 | Salon | 理发室 | Cable | Cable tray replacement | 44 | m² | 380 | 16720 | 22 | ⚠ Approved qty: 22
11 | Salon | 理发室 | Ceiling repair | Plasterboard ceiling void closure | 22 | m² | 190 | 4180 | 22
11 | Salon | 理发室 | Compliance | Re-inspection fee (lump sum) | 1 | item | 5000 | 5000 | 1
14 | Main Entrance | 入口 | Structural | Epoxy crack injection (lump sum) | 1 | item | 45000 | 45000 | 1
14 | Main Entrance | 入口 | Concrete repair | Concrete beam soffit render | 28 | m² | 780 | 21840 | 12 | ⚠ Approved qty: 12
14 | Main Entrance | 入口 | Temp. works | Temporary propping removal (lump sum) | 1 | item | 8500 | 8500 | 1
14 | Main Entrance | 入口 | Additional | Structural vibration monitoring system | 1 | item | 12000 | 12000 | 0 | ⚠ NOT in approved scope
CONTRACTOR'S TOTAL | [7 empty] | 308540
⚠ Rows highlighted in red: contractor quantity exceeds inspector-approved quantity, or work is not in approved scope.